## Roadmap
ID | Feature | Description | Category | Status | Priority | Difficulty | Effort (hrs) | Impact | Score | Owner | Source | Notes | Date added
F-001 | Score selection with clickable tiers | Pick a target score (200–800); tier pills (≤500/501–600/601–700/701–800) are tappable shortcuts. | Core | Shipped | P0 | S | 4 | 4 | 20 | Joshua | Spec PDF |  | 2026-04-29
F-002 | Tiered question pools | Test draws from difficulty buckets matching the target score. | Core | Shipped | P0 | M | 4 | 5 | 20 | Joshua | Spec PDF |  | 2026-04-29
F-003 | 30-question test with G/Y/R signal | Each question gets a green/yellow/red confidence signal — the core of the product. | Core | Shipped | P0 | L | 8 | 5 | 15 | Joshua | Spec PDF |  | 2026-04-29
F-004 | Live timer + total time | Sticky-header timer during the test, total time on results. | Core | Shipped | P1 | S | 3 | 4 | 20 | Joshua | Spec PDF |  | 2026-04-29
F-005 | Inline error states (no alerts) | Errors render in the UI rather than blocking modal dialogs. | Core | Shipped | P1 | S | 3 | 3 | 15 | Joshua | Internal |  | 2026-04-29
F-006 | Results bento (Mastery/Correct/Lucky/Review) | Four-tile breakdown — true mastery vs. lucky vs. to-review. | Core | Shipped | P0 | M | 4 | 5 | 20 | Joshua | Spec PDF |  | 2026-04-29
F-007 | Walkthrough review with explanations | Click-through review of every non-mastery question with the explanation. | Core | Shipped | P0 | L | 8 | 5 | 15 | Joshua | Spec PDF |  | 2026-04-29
F-008 | Share my score (image) | Generates a 1080×1080 share-card PNG with score + breakdown. | Growth | Shipped | P1 | M | 4 | 4 | 16 | Joshua | Spec PDF |  | 2026-04-29
F-009 | Copy review link (URL) | Encodes the attempt in a URL so you can send a review to a friend. | Growth | Shipped | P1 | M | 4 | 4 | 16 | Joshua | Internal |  | 2026-04-29
F-010 | Save trouble problems → PDF | Compiles every non-mastery question with explanations into one printable PDF. | Core | Shipped | P1 | M | 4 | 4 | 16 | Joshua | Spec PDF |  | 2026-04-29
F-011 | History (past attempts) | Persistent attempt history with open / re-share / delete / export. | Core | Shipped | P1 | L | 8 | 4 | 12 | Joshua | Internal |  | 2026-04-29
F-012 | Custom tailored test | Re-test that drills topics from non-mastery items. | Core | Shipped | P1 | M | 4 | 4 | 16 | Joshua | Spec PDF |  | 2026-04-29
F-013 | Admin dashboard with filters + actions | Wide table view of every question — filter by state/source/topic, Publish/Unpublish/Edit per row. | Admin | Shipped | P0 | L | 10 | 5 | 15 | Joshua | Internal |  | 2026-04-29
F-014 | Question schema + provenance | state (live/unpublished/needs-review), source (human-curated/ai-generated), uploader email. | Content | Shipped | P0 | M | 4 | 5 | 20 | Joshua | Internal |  | 2026-04-29
F-015 | 100 AI-generated questions (needs-review) | Pilot batch in needs-review state, awaiting admin audit before going live. | Content | Shipped | P1 | L | 6 | 4 | 12 | Joshua | Internal |  | 2026-04-29
F-016 | Magic-link login (email) | Email-only auth via Resend; HttpOnly signed JWT cookies; 30-day sessions. | Auth | Shipped | P0 | L | 8 | 5 | 15 | Joshua | Internal |  | 2026-04-29
F-017 | Roles + admin gating | user vs. admin roles. Admin allowlist for joshua@sortino.co + mweber0204@gmail.com. | Auth | Shipped | P0 | M | 4 | 5 | 20 | Joshua | Internal |  | 2026-04-29
F-018 | Resend integration + verified domain | noreply@studysignal.ai sends magic-link emails; rate-limited per email. | Infra | Shipped | P0 | M | 3 | 4 | 16 | Joshua | Internal |  | 2026-04-29
F-019 | Mobile-first responsive design | Safe-area insets, touch baseline, hover-on-touch override, breakpoint ladder. | Core | Shipped | P0 | L | 8 | 5 | 15 | Joshua | Internal |  | 2026-04-29
F-020 | Auth UI in distinct aesthetic | Compact centered card with halo glow — visually distinct from test cards. | Auth | Shipped | P1 | M | 3 | 3 | 12 | Joshua | Internal |  | 2026-04-29
F-021 | Ship to studysignal.ai (custom domain) | Production deploy, DNS at Hover, SSL via Let's Encrypt. | Infra | Shipped | P0 | M | 3 | 4 | 16 | Joshua | Internal |  | 2026-04-29
F-022 | Audit the 100 AI questions | Manual review pass: for each AI-generated question, verify answer key, promote to live. | Content | Next up | P0 | L | 10 | 5 | 15 | Joshua | Internal | Filter admin → needs-review + ai-generated, work through them. | 2026-04-29
F-023 | Supabase database setup | Replace in-memory dev store with Postgres. Run db/001_initial_schema.sql. | Infra | Next up | P0 | M | 3 | 5 | 20 | Joshua | Internal | Steps documented in BACKEND-SETUP.md. | 2026-04-29
F-024 | Cross-device attempt sync | Save attempts to Supabase so history follows the user across browsers/devices. | Infra | Next up | P1 | L | 6 | 4 | 12 |  | Internal | Depends on Supabase being live (F-023). | 2026-04-29
F-025 | Admin allowlist via DB (not code) | Move ADMIN_EMAILS Set out of source. Admin grants happen via SQL update. | Admin | Next up | P2 | S | 2 | 3 | 15 |  | Internal | Depends on F-023. | 2026-04-29
F-026 | Sharper 'Similar problems' tailored test | Broaden pool to all non-(green-and-correct) items; pick non-identical questions on same topic+difficulty. | Core | Next up | P1 | M | 4 | 4 | 16 |  | Spec PDF |  | 2026-04-29
F-027 | Challenge a friend (send a test) | Encode a fixed test setup in a URL; friend takes the same questions; results comparison. | Growth | Next up | P1 | M | 5 | 4 | 16 |  | Spec PDF |  | 2026-04-29
F-028 | Public signup flow polish | Already works; needs onboarding-friendly copy + first-test handholding for non-admin users. | Auth | Next up | P1 | S | 2 | 4 | 20 |  | Internal |  | 2026-04-29
F-029 | Generate 1000 more AI questions | Continue batches of 100 with the same self-validation methodology. Full bank target ~1100. | Content | Backlog | P1 | XL | 30 | 5 | 10 |  | User feedback | Wait for F-022 to validate quality bar first. | 2026-04-29
F-030 | Reading + writing sections | Currently math-only. Add the two verbal sections of the SAT. | Content | Backlog | P2 | XL | 40 | 5 | 10 |  | Internal |  | 2026-04-29
F-031 | ACT mode (separate test format) | ACT scoring + question pool + section structure. | Core | Backlog | P2 | L | 16 | 4 | 12 |  | Internal |  | 2026-04-29
F-032 | Practice mode (no timer, no scoring) | Drill mode for low-pressure repetition. | Core | Backlog | P2 | S | 3 | 3 | 15 |  | Internal |  | 2026-04-29
F-033 | Adaptive difficulty | Adjust the pool mid-test based on early-question signals. | Core | Backlog | P2 | XL | 30 | 4 | 8 |  | Internal |  | 2026-04-29
F-034 | Daily streak / habit tracking | Streak counter, daily reminder, calendar heatmap. | Growth | Backlog | P2 | M | 5 | 3 | 12 |  | Internal |  | 2026-04-29
F-035 | Weekly email digest | Personalized rundown of weak topics + recommended drills. | Growth | Backlog | P2 | M | 6 | 3 | 12 |  | Internal |  | 2026-04-29
F-036 | Progress visualization over time | Score trajectory, mastery-by-topic heatmap, time-spent. | Core | Backlog | P2 | L | 10 | 4 | 12 |  | Internal |  | 2026-04-29
F-037 | Question favoriting + notes | Star a question; attach a personal note; review favorites later. | Core | Backlog | P3 | S | 3 | 2 | 10 |  | Internal |  | 2026-04-29
F-038 | Spaced repetition for missed | Re-surface missed questions on Leitner-box schedule. | Core | Backlog | P2 | L | 12 | 4 | 12 |  | Internal |  | 2026-04-29
F-039 | PWA + offline support | Service worker + manifest. Already responsive — needs caching strategy. | Infra | Backlog | P2 | L | 10 | 3 | 9 |  | Internal |  | 2026-04-29
F-040 | Onboarding tutorial | First-run walkthrough explaining the green/yellow/red mechanic. | Growth | Backlog | P2 | M | 5 | 3 | 12 |  | Internal |  | 2026-04-29
F-041 | Marketing site | Public-facing landing page with positioning, screenshots, pricing. | Growth | Backlog | P3 | L | 16 | 3 | 9 |  | Internal |  | 2026-04-29
F-042 | Stripe integration (paid tier) | Free tier vs. paid (e.g., unlimited tests, advanced stats). | Infra | Backlog | P3 | L | 14 | 4 | 12 |  | Internal |  | 2026-04-29
F-043 | Question stats dashboard | Admin: cohort-level stats per question — % correct, signal distribution, weak topics. | Admin | Backlog | P2 | M | 5 | 3 | 12 |  | Internal |  | 2026-04-29
F-044 | Bulk import questions | Admin: paste/upload CSV or JSON to add questions in batch. | Admin | Backlog | P2 | M | 4 | 3 | 12 |  | Internal |  | 2026-04-29
F-045 | Subject-specific scoring breakdown | Show per-section scoring estimate (math vs. reading vs. writing) on results. | Core | Backlog | P2 | M | 4 | 3 | 12 |  | Internal | Depends on F-030. | 2026-04-29
F-046 | A/B testing framework | Feature-flag system + cohort assignment for product experiments. | Infra | Backlog | P3 | L | 14 | 3 | 9 |  | Internal |  | 2026-04-29
F-047 | Comparison to peers | Cohort percentile + benchmark scores from anonymized aggregate. | Future | Idea | P3 | L | 14 | 3 | 9 |  | Internal |  | 2026-04-29
F-048 | Tutor mode (AI help) | Embedded AI tutor — explain stuck problems, generate hints. | Future | Idea | P3 | XL | 40 | 4 | 8 |  | Internal |  | 2026-04-29
F-049 | Class / teacher dashboard | Teachers create cohorts, assign tests, see aggregate progress. | Future | Idea | P3 | XL | 50 | 4 | 8 |  | Internal |  | 2026-04-29
F-050 | Native mobile app | iOS + Android wrappers — push notifications, deep links, App Store presence. | Future | Idea | P3 | XL | 80 | 3 | 6 |  | Internal | PWA (F-039) likely covers 80% of value at 10% of cost. | 2026-04-29

## Legend
Roadmap legend
Status
Shipped | Built and live on studysignal.ai.
Next up | Committed for the next batch of work.
Backlog | Known-want, no immediate timeline.
Idea | Speculative — not committed.
Blocked | Needs a decision or upstream work.
Priority
P0 | Critical — ship immediately.
P1 | High — within next batch.
P2 | Medium — known-want, no urgency.
P3 | Low — nice to have.
Difficulty
XS | Less than 1 hour.
S | Less than 4 hours.
M | Less than 1 day.
L | Multi-day, single chunk of work.
XL | A week or more, often multiple parts.
Category
Core | The actual study experience.
Content | Question pipeline + bank.
Admin | Internal admin tooling.
Auth | Sign-in, accounts, roles.
Infra | Backend, deployment, ops.
Growth | Marketing, sharing, retention.
Future | Speculative, longer-term.
Score
Formula | Impact × difficulty-bonus (XS=6 → XL=2). Higher = ship-sooner candidate.
Range | 1–30. Use as a sort key, not a hard rule.